## Sheet1
Date | Summary | Description
2014-07-18 | Initial setup | Created all documentation, created project solution
2014-07-18 | Added project to github | https://github.com/ELepolt/ATO_Kanban.git
2014-07-18 | Requirements | Redid requirements as a group
2014-07-18 | Final update to github.
2014-07-21 | Project setup | Created all classes, database, installed all packagages (Bootstrap, AngularJS)
2014-07-21 | Home page | Created index.html and backend app.js to show todos in their corresponding columns
2014-07-22 | Claiming action | Created the functionality to move a todo from one status to another
2014-07-23 | Set up Sogeti Github | If the username and password are forgotten, ask Evan.Lepolt@gmail.com
2014-07-23 | Added ability to add new Todo | Modal pops up with necessary fillings. More work should be done so that stuff like 'Email ATO' doesn't show up with 'Is Public' is not checked
2014-07-24 | Set up login and cookies | Users can now log in and it is saved as a cookie variable
2014-07-25 | Claiming/Revise/Approve functionality | Users can now claim objects, and only they can complete them. Revision sends todos back to the 'Claimed' column. Approval adds a FinishDate in DB